Department of Energy and National Science Foundation

Status Review of the VERITAS Project

WHEN:	November 30 – December 1, 2004

WHERE:	Amado, Arizona

REVIEW COMMITTEE:

This review Committee is shown below.

| DOE | NSF | Consultants |
| --- | --- | --- |
| Dan Lehman (observer) | Pat Bautz | Ken Johns |
| Kathy Turner | Vernon Pankonin | Paul La Marche |

SUMMARY:

The VERITAS project appears to be on cost and schedule and is progressing well.  No technical issues exist.  However, a quantitative assessment of project status was not made.  The Committee recommended that a risk analysis be performed to ensure completion of the project on schedule and within the available funding.  A number of recommendations were also made involving project management tools and planning.

INTRODUCTION:

The Very Energetic Radiation Imaging Telescope Array System (VERITAS) is a gamma ray telescope array under construction on Kitt Peak, near Tucson, AZ.  VERITAS will provide the ground-based capability to study extremely energetic gamma-rays, ranging in energy from 50 GeV to 50 TeV, potentially produced from a variety of astrophysical sources. The gamma-rays are observed from the light they induce as they interact with the Earth’s atmosphere.

REVIEW PURPOSE:

The charge for the review was to determine the status of the project relative to the baseline and the progress since the February 2004 review.  In particular, the review was to address the technical, cost, schedule and management aspects of the project to the subproject level and including subaward performance.  The project’s risk assessment was reviewed along with the plans for the scientific operating phase.  There were tours of the VERITAS site on Kitt Peak and telescope #1 at the Whipple Observatory base camp.

PROJECT STATUS (as of September 30, 2004):

Total Estimated Cost (TEC)	$13.145 million

DOE	$4.799 million

NSF	$6.643 million

SAO	$1.079 million

Foreign	$0.624 million

Percent Complete in terms of Cost 	39 percent

Percent Complete in terms of Schedule	33 percent

Remaining Management Reserve	$1.155 million

Management Reserve as % of Costs To Go	16 percent

Schedule:

Performance Baseline Approved 	June 2, 2004

Project Completion (planned) 	September 30, 2006

TECHNICAL:

The team has made a lot of progress since the last review.  There are no outstanding technical hurdles.  Telescope #1 has been erected at the Whipple base camp and will be operated there for the next year before it moves to the permanent site on Kitt Peak.  The tour of telescope #1 was impressive and provides strong evidence that the project faces no outstanding technical problems.  Good technical progress was exhibited by all subprojects.  The facility at Kitt Peak appears to be progressing well.  It may be a month or so behind schedule, but this shouldn’t affect the project.  A few critical areas such as the flash analog to digital converter (FADC) system and focus boxes would greatly benefit from additional manpower from the collaboration.  Management reserve may need to be used for these activities.

- The Committee recommended that the project office perform a contingency analysis and take into account the available management reserve versus time before making a decision to add sleeping quarters at Kitt Peak to the project scope.

COST AND SCHEDULE:

The project appeared to be on schedule, within budget and progressing well, although the lack of the usual project management tools (such as an earned value management system) made it difficult to quantitatively evaluate the project performance in detail.  The Committee felt that the project office would benefit from producing and analyzing data on actual versus scheduled technical progress, costs and manpower.  In particular, the manpower required to complete the project versus that scheduled should be examined in detail.  This assessment should include the manpower required to carry out the tasks in the subprojects that are contained in the subawards.

MANAGEMENT:

The team made progress such as completing the prototype and telescope #1 and the start of the facility at Kitt Peak.  The project office is oriented towards getting the job done.  The collaboration works together cooperatively and seems to be functioning well.  There is good communication between the project office, subgroups and the overall collaboration.

A plan must be developed for demonstrating how the technical capabilities of the telescope which are associated with project completion will be achieved.

It appeared to the Committee that the financial and schedule information is not being utilized by management as much as it could be while making key decisions.

The contingency held by the project office appears to be sufficient to complete the project and only a few large cost items remain to be purchased.  Most of this contingency is assigned to individual WBS subsystems.  The Committee encouraged the project office to centralize the remaining contingency funds and use these funds to help support critical areas, thereby ensuring successful project completion.

RISK:

Risks and critical path items were identified and discussed.  The Committee was concerned about risks in terms of cost and schedule.

- The Committee recommended that a quantitative risk analysis be developed which addresses scope, cost and schedule and includes decision points.  This would be useful in helping the project take actions and have backup plans in hand before problems arise.

OPERATING PHASE PLANS:

The scientific program including key observation goals and maintenance was presented. The science of VERITAS is excellent and complementary to other telescopes.

- The Committee recommended that a high priority for the project office should be the development of a detailed operations plan (e.g. resource loaded schedule) including both operations and observation manpower.  Adequate spares of key components should also be considered.

ADDITIONAL RECOMMENDATIONS:

- Develop a plan for the project to go forward from the start of FY 2005 through the end of FY 2006 by March 15, 2005.  This should be done in terms of technical scope, cost, schedule, and resources (manpower & funds).  This plan must include the definition of completion of the construction phase of the project and the means of verifying successful completion.

- Develop a more detailed operations concept by March 15, 2005.

- Develop a risk assessment and mitigation plan by March 15, 2005.

- Submit a corrected 4th quarter FY 2004 quarterly report to the agencies.  Future reports should show performance metrics for each subproject as well as for the overall project.

ACTION ITEMS:

- The agencies should conduct a follow-up review in the Washington, D.C. area by

March 31, 2005.